## SSDMS 15, 21, 23, 26
Type | Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
Frontend (AB) | SSDMS-15 | 11 | T1 | Existing code Understanding | 1.5 |  | 1.5
| SSDMS-15 |  | T2 | Create necessary skeleton for making Assessment Body status Table | 0.5 |  | 0.5
| SSDMS-15 |  | T3 | Create Divisions for AB status table | 0.5 |  | 0.5
| SSDMS-15 |  | T4 | Create basic structure of Table | 0.5 |  | 0.5
| SSDMS-15 |  | T5 | Label Entities using JS | 1 |  | 1
| SSDMS-15 |  | T6 | Create Edit feature for editing Affiliation forms | 2 |  | 2
| SSDMS-15 |  | T7 | Function to perform Edit option | 2 |  | 2
| SSDMS-15 |  | T8 | Receive Data from Backend | 1 |  | 1
| SSDMS-15 |  | T9 | Unit Testing | 0.5 |  | 0.5
| SSDMS-15 |  | T10 | Code Review & Feedback | 0.5 |  | 0.5
| SSDMS-15 |  | T11 | Incorporate Feedback | 0.5 |  | 0.5
| SSDMS-15 |  | T12 | SVN Commit | 0.5 |  | 0.5
Backend (AB) | SSDMS-21 | 12.5 | T1 | Existing code Understanding | 1.5 |  | 1.5
| SSDMS-21 |  | T2 | Create Dummy DB | 1 |  | 1
| SSDMS-21 |  | T3 | Estabilish connection between Frontend & Backend | 2 |  | 2
| SSDMS-21 |  | T4 | Map Entities of DB to table columns(Frontend) | 2 |  | 2
| SSDMS-21 |  | T5 | Comment Column should be changed by input of SCGJ | 2 |  | 2
| SSDMS-21 |  | T6 | On click of Edit icon Affiliation form Controller should be called | 2 |  | 2
| SSDMS-21 |  | T7 | Unit Testing | 0.5 |  | 0.5
| SSDMS-21 |  | T8 | Code Review & Feedback | 0.5 |  | 0.5
| SSDMS-21 |  | T9 | Incorporate Feedback | 0.5 |  | 0.5
| SSDMS-21 |  | T10 | SVN Commit | 0.5 |  | 0.5
Frontend (TP) | SSDMS-23 | 11 | T1 | Existing code Understanding | 1.5 |  | 1.5
| SSDMS-23 |  | T2 | Create necessary skeleton for making Assessment Body status Table | 0.5 |  | 0.5
| SSDMS-23 |  | T3 | Create Divisions for AB status table | 0.5 |  | 0.5
| SSDMS-23 |  | T4 | Create basic structure of Table | 0.5 |  | 0.5
| SSDMS-23 |  | T5 | Label Entities using JS | 1 |  | 1
| SSDMS-23 |  | T6 | Create Edit feature for editing Affiliation forms | 2 |  | 2
| SSDMS-23 |  | T7 | Function to perform Edit option | 2 |  | 2
| SSDMS-23 |  | T8 | Receive Data from Backend | 1 |  | 1
| SSDMS-23 |  | T9 | Unit Testing | 0.5 |  | 0.5
| SSDMS-23 |  | T10 | Code Review & Feedback | 0.5 |  | 0.5
| SSDMS-23 |  | T11 | Incorporate Feedback | 0.5 |  | 0.5
| SSDMS-23 |  | T12 | SVN Commit | 0.5 |  | 0.5
Backend (TP) | SSDMS-26 | 9 | T1 | Existing code Understanding | 1.5 |  | 1.5
| SSDMS-26 |  | T2 | Create Dummy DB | 1 |  | 1
| SSDMS-26 |  | T3 | Estabilish connection between Frontend & Backend | 0.5 |  | 0.5
| SSDMS-26 |  | T4 | Map Entities of DB to table columns(Frontend) | 1 |  | 1
| SSDMS-26 |  | T5 | Comment Column should be changed by input of SCGJ | 1.5 |  | 1.5
| SSDMS-26 |  | T6 | On click of Edit icon Affiliation form Controller should be called | 1.5 |  | 1.5
| SSDMS-26 |  | T7 | Unit Testing | 0.5 |  | 0.5
| SSDMS-26 |  | T8 | Code Review & Feedback | 0.5 |  | 0.5
| SSDMS-26 |  | T9 | Incorporate Feedback | 0.5 |  | 0.5
| SSDMS-26 |  | T10 | SVN Commit | 0.5 |  | 0.5
| Total | 43.5