## SSDMS 15, 21, 23, 26
Type | Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
Frontend (AB) | SSDMS-15 | 13.5 | T1 | Understand the existing code | 1.5 |  | 1.5
| SSDMS-15 |  | T2 | Create necessary skeleton for making Assessment Body application status Table | 0.5 |  | 0.5
| SSDMS-15 |  | T3 | Create layout of HTML page | 0.5 |  | 0.5
| SSDMS-15 |  | T4 | Create ui grid table for application status | 1 |  | 1
| SSDMS-15 |  | T5 | Label Entities using JS | 1 |  | 1
| SSDMS-15 |  | T6 | Create Edit feature for editing Affiliation forms | 2 |  | 2
| SSDMS-15 |  | T7 | Function to perform Edit option | 2 |  | 2
| SSDMS-15 |  | T8 | Receive data from Backend & populate in Profile Creation page | 1.5 |  | 1.5
| SSDMS-15 |  | T9 | Check Application Status (Approved/ Rejected/ Pending) | 0.5 |  | 0.5
| SSDMS-15 |  | T10 | Open profile creation page | 1 |  | 1
| SSDMS-15 |  | T11 | Change Status to pending | 0.5 |  | 0.5
|  |  | T12 | Unit Testing | 0.5 |  | 0.5
|  |  | T13 | Code Review & Feedback | 0.5 |  | 0.5
| SSDMS-15 |  | T14 | Incorporate Feedback | 0.5 |  | 0.5
Backend (AB) | SSDMS-21 | 12 | T1 | Understand the existing code | 1.5 |  | 1.5
| SSDMS-21 |  | T2 | Create Dummy DB | 1 |  | 1
| SSDMS-21 |  | T3 | Estabilish connection between Frontend & Backend | 2 |  | 2
| SSDMS-21 |  | T4 | Map Entities of DB to table columns(Frontend) | 2 |  | 2
| SSDMS-21 |  | T5 | Comment Column should be changed by input of SCGJ | 2 |  | 2
| SSDMS-21 |  | T6 | On click of Edit icon Affiliation form Controller should be called | 2 |  | 2
| SSDMS-21 |  | T7 | Unit Testing | 0.5 |  | 0.5
| SSDMS-21 |  | T8 | Code Review & Feedback | 0.5 |  | 0.5
| SSDMS-21 |  | T9 | Incorporate Feedback | 0.5 |  | 0.5
Frontend (TP) | SSDMS-23 | 13 | T1 | Understand the existing code | 1.5 |  | 1.5
| SSDMS-23 |  | T2 | Create necessary skeleton for making Training Partner application status Table | 0.5 |  | 0.5
| SSDMS-23 |  | T3 | Create layout of HTML page | 0.5 |  | 0.5
| SSDMS-23 |  | T4 | Create ui grid table for application status | 0.5 |  | 0.5
| SSDMS-23 |  | T5 | Label Entities using JS | 1 |  | 1
| SSDMS-23 |  | T6 | Create Edit feature for editing Affiliation forms | 2 |  | 2
| SSDMS-23 |  | T7 | Function to perform Edit option | 2 |  | 2
| SSDMS-23 |  | T8 | Receive data from Backend & populate in Profile Creation page | 1.5 |  | 1.5
| SSDMS-23 |  | T9 | Check Application Status (Approved/ Rejected/ Pending) | 0.5 |  | 0.5
| SSDMS-23 |  | T10 | Open profile creation page | 1 |  | 0.5
| SSDMS-23 |  | T11 | Change Status to pending | 0.5 |  | 0.5
| SSDMS-23 |  | T12 | Unit Testing | 0.5 |  | 0.5
| SSDMS-23 |  | T13 | Code Review & Feedback | 0.5 |  | 0.5
| SSDMS-23 |  | T14 | Incorporate Feedback | 0.5 |  | 0.5
Backend (TP) | SSDMS-26 | 12 | T1 | Understand the existing code | 1.5 |  | 1.5
| SSDMS-26 |  | T2 | Create Dummy DB | 1 |  | 1
| SSDMS-26 |  | T3 | Estabilish connection between Frontend & Backend | 2 |  | 2
| SSDMS-26 |  | T4 | Map Entities of DB to table columns(Frontend) | 2 |  | 2
| SSDMS-26 |  | T5 | Comment Column should be changed by input of SCGJ | 2 |  | 2
| SSDMS-26 |  | T6 | On click of Edit icon Affiliation form Controller should be called | 2 |  | 2
| SSDMS-26 |  | T7 | Unit Testing | 0.5 |  | 0.5
| SSDMS-26 |  | T8 | Code Review & Feedback | 0.5 |  | 0.5
| SSDMS-26 |  | T9 | Incorporate Feedback | 0.5 |  | 0.5
| Total | 50.5
Note on E4: Pranjal Kumar Singh: HTML divs, sections and colr, padding
Note on E31: Pranjal Kumar Singh: HTML divs, sections and colr, padding