## Name 1
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
SSDMS 1 2 3 4 5 |  | T1 | Understanding "WHY" of the story (Bussiness Rule): *A user must be provided with login page so that he/she can access their respective pages. *When user entered the credential on login page both server side and client side validation should be performed,so that only authentic user logs in web app. | 2 |  | 2
|  | T2 | Forward and Backward Linkage: >In backward linkage a database must be defined as per the schema defined and linking a DB to FE so that server side validation is to be done. >In forward linking/routing the request so that credentialis is to be validated from backend database(i.e )server. | 2 |  | 2
|  | T3 | Work Flow: >Making a block diagram of entire journey of the code so that scope and approach becomes clear. | 2 |  | 2
|  | T4 | Technical Understanding of How things works in backend and frontend. Angular ng route,http post requests | 3 |  | 2
0
|  | T5 | Making a login page as aggreed in gd i.e fixing minor bugs in visual i.e making required changes in login.css | 2 |  | 2
|  | T6 | Making a stable bakend re defining bakend databse schema as per reqiured database. | 2 |  | 2
|  | T7 | Making a connection with backend database server. | 2 |  | 2
|  | T8 | Fetching the req values from database based on respective username and password(i.e app_id,app_status and user_type) | 2 |  | 2
|  | T9 | To understand how credential moves to backend and invoke server so that credentials are to be validated. | 3 |  | 3
|  | T10 | Intergrating login button funtionality with ng route services on ng click. | 3 |  | 3
|  | T11 | Moving the credential to backend via http post methods | 3 |  | 3
|  | T12 | Integrating FE and BE | 2 |  | 2
|  | T13 | Unit testing and code review | 1 |  | 1
|  | T14 | Incorporate code review changes (if any) | 2 |  | 2
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 2
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 3
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 4
Story ID | Story Estimate | Task ID |  | Task Description | Planned Hours | Hours Burnt | Remaining Hours
|  |  | Technical understanding | ng route | 2 |  | 2
|  |  |  | http.post | 1 |  | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 5
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours | Status
|  | T1 | Understanding "WHY" of the story (Bussiness Rule):
SSDMS 1 2 3 4 5 |  |  | *A user must be provided with login page so that he/she can access their respective pages. *When user entered the credential on login page both server side and client side validation should be performed,so that only authentic user logs in web app. | 2 |  | 2 | Done
|  | T2 | Forward and Backward Linkage:
|  |  | >In backward linkage a database must be defined as per the schema defined and linking a DB to FE so that server side validation is to be done. >In forward linking/routing the request so that credentialis is to be validated from backend database(i.e )server. | 2 |  | 2 | Done
|  | T3 | Work Flow and Block Diagram
|  |  | >Making a block diagram of entire journey of the code so that scope and approach becomes clear. | 2 |  | 2 | Done
| 23.5 | T4 | Technical Understanding of How things works in backend and frontend. Angular ng route,http post requests | 0 |  | 0 | Done
|  | T5 | Making a login page as aggreed in gd i.e fixing minor bugs in visual i.e making required changes in login.css | 1 | 0.5 | 0.5
|  | T6 | Perform/check clent side validations are as per acceptance criteria. | 1 |  | 1
|  | T7 | Make a stable bakend re-defining bakend database schema and java files as per reqiured database. >Making a database as per the schema defined. >Making required java file for backend. | 3 | 2 |  | IN DEV
|  | T8 | Making a connection with backend database server/jdbc connectivity. | 0.5 | 0.5 | 0 | Done
|  | T9 | Fetching the req values from database | 3 | 1 | 2 | IN DEV
|  | T10 | To understand how credential moves to backend and invoke server so that credentials are to be validated. | 4 | 2 | 2 | IN DEV
|  | T11 | Make login button functionaL | 1 | 0.5 | 0.5 | IN DEV
|  | T12 | Intergrating login button funtionality with ng route services on ng click. | 4 |  | 4
|  | T13 | Getting a response from backend database server (http.post()) | 3 |  | 3
|  | T14 | Integrating FE and BE | 0 |  | 0
|  | T15 | Unit testing | 1 |  | 1
|  | T16 | Code review and Incorporate feedback | 2 |  | 2
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
4