## Data Import
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours | Status
|  |  | Understand Story: Import history table to be populated so that the user can view and download all the recent excel sheet uploaded. |  |  | 0 | Done
|  |  | Develop Technical Understanding : JavaScript |  |  |  | Done
AngularJS
Angular UI-grid
java
|  |  | Backward linkages: Uploaded Excel sheets and its path to show in Import history table's view file and file name column respectively. |  |  |  | Done
|  |  | Block Diagrams of the whole journey |  |  |  | Done
SSDMS-47&48 | 22 | T-1 | Write Code for Ui-grid table(Angularjs, Angular UI-grid) | 2 | 2 | 0 | In QA
|  | T-2 | Add clickable image in Last Column(view File) of Ui-grid table | 1 | 1 | 0
|  | T-3 | Create json objects in .json file according to the column definition | 1 | 1 | 0
|  | T-4 | receive value from back end - http.get | 1 | 1 | 0
|  | T-5 | Establish Database connection | 2 | 2 | 0
|  | T-6 | Create a dummy table in the Database | 1 | 1 | 0
|  | T-7 | Receive Values from the Database | 1 | 1 | 0
|  | T-8 | Send response to front end | 1 | 1 | 1
|  | T-9 | Method to download CSV file on user machine | 6 | 4 | 2
|  | T-10 | Call that method on click of csv download image | 2 |  | 2
|  | T-11 | Unit Testing | 1 |  | 1
|  | T-12 | Review and Feedback incorporation | 1 |  | 1
|  | T-13 | Rework | 2 |  | 2
SSDMS-44 | 10 | T-1 | Write HTML of the layout (divs , color, margin placing) | 4 | 4 | 0 | In QA
|  | T-2 | integrate upload drop down and button | 4 |  | 4
|  | T-3 | Styling | 2 | 1 | 1
[5 empty] | Total = | 14