## Name 1
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 2
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 3
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 4
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 5
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours | Status | Remarks | DateOfCompletion
SSDMS-50 | 18 | T50-1 | Understand bigger picture | 1 | 1 | 0 | Done |  | 2017-07-04
|  | T50-2 | Understand 'our' and 'their' database schema | 2 | 2 | 0 | Done
|  | T50-3 | Understand current excel sheets and drawing inferences | 2 | 1 | 1 | Done | Saved 1 hour
|  | T50-4 | Create MySql queries | 6 | 2 | 4 | Done | Saved 4 hour to be used in Testing
|  | T50-5 | Create dummy tables for testing | 4 | 6 | -2 | Continuing | Used 6 hours on 5/7/2017 | 2017-05-07
|  | T50-6 | Test created queries in created tables | 2 |  | 2
|  |  | Buffer Time | 1 |  | 1
|  |  | Total Hours Burnt | 12
|  |  | Hours Remaining | 6