## Data Import
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
|  |  | Story Understanding: Import history table to be populated so that the user can view and download all the recent excel sheet uploaded. |  |  | 0
Technical Understanding : JavaScript
AngularJS
Angular UI-grid
java
Backward linkages: Uploaded Excel sheets and its path to show in Import history table's view file and file name column respectively.
Block Diagrams of the whole journey
SSDMS-47&48 | 22 | T-1 | Write Code for Ui-grid table(Angularjs, Angular UI-grid) | 2 |  | 2
|  | T-2 | Add clickable image in Last Column(view File) of Ui-grid table | 1 |  | 1
|  | T-3 | Create json objects in .json file according to the column definition | 1 |  | 1
|  | T-4 | Pass json objects in http.get written in code(Dynamic Table) | 1 |  | 1
|  | T-5 | Establish Database connection | 2 |  | 2
|  | T-6 | Create a dummy table in the Database | 1 |  | 1
|  | T-6 | Receive Values from the Database | 1 |  | 1
|  | T-7 | Populate values on the frontend | 1 |  | 1
|  | T-8 | Write logic of on-click image functionality i.e, view uploaded excel file, in services | 6 |  | 6
|  | T-9 | Integrate the Code | 2 |  | 2
|  | T-10 | Unit Testing | 1 |  | 1
|  | T-11 | Review and Feedback incorporation | 1 |  | 1
|  | T-12 | Rework | 2 |  | 2
SSDMS-44 | 8 | T-1 | Write HTML of the Data Import epic(integrating the whole code) | 4 |  | 4
|  | T-2 | Write css code to give the styling to the epic as per GD | 4 |  | 4
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0