## Sheet1
story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
Logout functionality
SSDMS-14 | 22 hrs. | T-01 | Understanding 'WHY' of the story? | 3 hrs |  | 3 hrs
|  | T-02 | Understanding forward and backward linkages. | 6 hrs |  | 6 hrs
|  | T-03 | Make block diagram of the entire code journey. | 2 hrs |  | 2 hrs
|  | T-04 | Technical Understanding of the story. Which languages (Angular,Bootstarp) is used to implement the story . | 6 hrs |  | 6 hrs
|  | T-05 | Unit Testing | 3 hrs |  | 3 hrs
|  | T-06 | Code Review | 1 hrs |  | 1 hrs
|  | T-07 | Incorporate code review comments. | 1 hrs |  | 1 hrs
Batch Assignment and Search option
SSDMS-15 | 40 hrs | T-01 | Understanding 'WHY' of the story? To make a Batch Assignment table including a search option. | 4 hrs | 4 hrs. | 0
|  | T-02 | Understanding forward and backward linkages. | 6 hrs | 6 hrs | 0
|  | T-03 | Make block diagram of the entire code journey. | 2 hrs | 2 hrs | 0
|  | T-04 | Technical Understanding of the story. Which languages (HTML) is used to implement the story . | 6 hrs | 6 hrs. | 0
|  | T-05 | Pick Batch-ID to be search from frontend. | 1 hr | 1 hr | 0
|  |  | Populate the table in the BA page below the search option. | 3 hr | 1 hr | 2 hr
|  | T-06 | Send Batch-ID to a Backend. | 2 hr |  | 2 hr
|  | T-07 | Receive data from database. | 3 hr |  | 3 hr
|  | T-08 | Implement database SQL queries. | 3 hr |  | 3 hr
|  | T-09 | Receive data sent by Database,SQL query. | 2 hr |  | 2 hr
|  | T-10 | Send data to frontend. | 2 hr |  | 2 hr
|  | T-11 | Receive detail of Batch-ID | 1 hr |  | 1 hr
|  | T-12 | Populate the table with data received from Backend. | 3 hr |  | 3 hr
|  | T-13 | Unit Testing | 2 hrs |  | 2 hrs
|  | T-14 | Code Review | 1 hrs |  | 1 hrs
|  | T-15 | Incorporate code review comments. | 2 hrs |  | 2 hrs