## Name 1
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 2
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 3
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 4
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 5
Type | Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
Frontend | SSDMS-6 | 14 | T1 | Understand the "why" of the story. | 1 | 1 | 0
|  |  | T2 | Understand forward and backward linkages . | 1 | 1 | 0
|  |  | T3 | Make the block diagram of the entire code journey | 2 | 2 | 0
|  |  | T4 | Make technical understanding where html and css is used | 4 | 4 | 0
|  |  | T5 | Development of signup page | 6 |  | 6
Frontend | SSDMS-6 | 7 | T1 | Understand forward and backward linkages | 0 | 0 | 0
|  |  | T2 | Understand the angular services | 3 |  | 3
|  |  | T3 | Write code to post the data on backend | 3 |  | 3
|  |  | T4 | Review and incorporate the changes | 1 |  | 1
Backend | SSDMS-6 | 5 | T1 | Understand the response from the backend | 1 |  | 1
|  |  | T2 | write the code to route the user to the page according to their role | 4 |  | 4
Review |  | 2 | T1 | Review and incorporate the changes | 2 |  | 2
0
|  | TOTAL | 28 |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0