## SSDMS 54,55,56
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours | Status
SSDMS 54,55,56 | 14.5 | T1 | Technical Understanding 1) Angular UI-Grid 2) AngularJS 3) Java 4) MySQL |  |  | 0 | Done
|  | T2 | Create a table using UI-grid. | 1 | 0 | 1 | Incomplete
|  | T3 | Connect the table to the DB and populate the values based on pre-defined parameters. | 2 | 0 | 2 | Incomplete
|  | T4 | Formulate an algorithm for determination of automatically recommending the Assessment Body. | 2 | 0 | 2 | Incomplete
|  | T5 | Integrate the algorithm in the Java code. | 1.5 | 0 | 1.5 | Incomplete
|  | T6 | Create a dropdown for facilitating manual selection and assignment of Assessment Body. | 1 | 0 | 1 | Incomplete
|  | T7 | Make the dropdown menu display the recommended Assessment Body by default. | 2 | 0 | 2 | Incomplete
|  | T8 | Create a confirm button and incorporate it in the UI-Grid table. | 1 | 0 | 1 | Incomplete
|  | T9 | Connect the backend functionality to the Confirm button. | 2 | 0 | 2 | Incomplete
|  | T10 | Unit Testing | 1 | 0 | 1 | Incomplete
|  | T11 | Code review | 0.5 | 0 | 0.5 | Incomplete
|  | T12 | Incorporate code review changes. | 0.5 | 0 | 0.5 | Incomplete
14.5
Story Understanding A non-assigned batches table should be made so that the product owner (SCGJ) may view the list of all the non-assigned batches. Also there should be an algorithm that automatically recommends the most suitable Assessment Body. Finally an assign button is needed so that the user may assign the Assessment Body to the batches.
Backward Linkages - 1) The meaning of the term 'non-assigned' should be clear so that the table may be populated without issues. 2) As soon as the training partner gets his application form approved his status should become 'non-assigned'. Forward Linkages - 1) As soon as the SCGJ user allots the Assessment Body for the batch, the batch should be moved from the 'non-assigned' to 'proposed' section.

## SSDMS 41
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours | Status
SSDMS 41 | 18 | T1 | Technical understanding- 1) AngularJS 2) JasperReport 3) Java |  |  | 0 | Done
|  | T2 | Create a JRXML file using JasperSoft studio. | 3 | 3 | 0 | In Progress
|  | T3 | Complile the JRXML file to Jasper Report template. | 2 | 2 | 0 | In Progress
|  | T4 | Fill the Jasper template with data from the database to generate a .jrprint file. | 3 | 0 | 3 | Incomplete
|  | T5 | Generate a PDF from the template. | 2 | 0 | 2 | Incomplete
|  | T6 | Create a download button and integrate it in the UI-grid table. | 1 | 0 | 1 | Incomplete
|  | T7 | Link the download button to the PDF generator function. | 2 | 0 | 2 | Incomplete
|  | T8 | Unit Testing | 1 | 0 | 1 | Incomplete
|  | T9 | Code review | 1 | 0 | 1 | Incomplete
|  | T10 | Incorporate code review changes | 1 | 0 | 1 | Incomplete
|  | T11 | Bug fixing | 2 | 0 | 2 | Incomplete
13
Story Understanding A PDF should be available to the product owner (SCGJ), so that he may download and view the application form for review purposes and then take action accordingly.
Backward Linkages - 1) Only the most relevant and absolutely necessary fields of both the application forms(AB & TP) should be shortlisted. 2) The DB should have the information filled by the applicant stored in it. 3) A grid table should be available on the front end so that the download button may be integrated into it. Forward Linkages -