## Name 1
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
Import Certificate
SSDMS - 62 | 20 | T-1 | Understand the bigger picture of the story. (Why Part ???) To provide a feature for Certificate Import. | 2 |  | 2
|  | T-2 | Create a Block Diagram. | 1 |  | 1
|  | T-3 | Create Textbox & Search button. | 2 |  | 2
|  | T-4 | Create Back-end using Java and Springboot. | 8 |  | 8
|  | T-5 | Create connection between Front-end & Back-end. | 4 |  | 4
|  | T-6 | Unit Testing & Debugging. | 3 |  | 3
Download Certificate
SSDMS - 64 | 13 | T-1 | Understand the bigger picture of the story. (Why Part ???) To provide a feature for Certificate Import. | 2 |  | 2
|  | T-2 | Create a Block Diagram. | 1 |  | 1
|  | T-3 | Create a Downlaod Button.(certificate) | 1 |  | 1
|  | T-4 | Create Back-end using Java and Springboot. | 4 |  | 4
|  | T-5 | Create connection between Front-end & Back-end. | 2 |  | 2
|  | T-6 | Unit Testing & Debugging. | 3 |  | 3
Search - Manage registration
SSDMS - 66 | 19.5 | T-1 | Understand the bigger picture of the story. (Why Part ???) To provide a search feature for Batch and details regarding the Batch | 2 |  | 2
|  | T-2 | Creating a Block Diagram. | 1 |  | 1
|  | T-3 | Create Search field & Search button. | 0.5 |  | 0.5
|  | T-4 | Create a table using Angular U-grid. For the Display of information. | 6 |  | 6
|  | T-5 | Create the connection between the Table and Database. | 4 |  | 4
|  | T-6 | Unit Testing & Debugging. | 2 |  | 2
48.5

## Name 2
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 3
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 4
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 5
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0