## Prateek and Arjita
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours | Done | Story Status
SSDMS-098*(Dashboard) | 27.5 Hours | T-01 | Understand the business | 0.5 | 0.5 | 0 | Done | Not Started
|  | T-02 | Understand the forward and backward linkages | 0.5 | 0.5 | 0 | Done
|  | T-03 | Create a block diagram(Work-Flow) | 0.5 | 0.5 | 0 | Done
|  | T-04 | Create basic HTML and CSS Structure - for page | 4 |  | 4 | Not Started
|  | T-05 | Implement Angular JS for dynamic Behaviour | 4 |  | 4 | Not Started
|  | T-06 | Implement Back-end logic for pannels | 2 |  | 2 | Not Started
|  | T-07 | Understand JSON objects for different charts | 1 |  | 1 | Not Started
|  | T-08 | Create High-charts | 10 |  | 10 | Not Started
|  | T-09 | Implement Back-end logic for high-charts | 1 |  | 1 | Not Started
|  | T-10 | Integrate the high charts into the dashboard | 2 |  | 2 | Not Started
|  | T-11 | Unit Testing | 1 |  | 1 | Not Started
|  | T-12 | Code Review | 1 |  | 1 | Not Started
26
SSDMS-100* (Home Page TP) | 20.5 Hours | T-01 | Understand the business | 0.5 | 0.5 | 0 | Done | IN DEV | 0
|  | T-02 | Understand the forward and backward linkages | 0.5 | 0.5 | 0 | Done |  | 0
|  | T-03 | Create the HTML and CSS structure | 4 | 1.5 | 2.5 | Done |  | 2.5
|  | T-04 | Create a block diagram(Work-Flow) | 0.5 | 0.5 | 0 | Done |  | 0
|  | T-05 | Understand UI-Grid | 2 | 0.5 | 1.5 | Done |  | 1.5
|  | T-06 | Create the structure of TP home page using UI Grid | 5 | 5 | 0 | Done |  | 0
|  | T-07 | Write SQL queries to fetch required data from tables in the DB | 4 | 4 | 0 | Done |  | 0
|  | T-08 | Receive sent response from SQL Queries in DTO | 2 | 2 | 0 | Done |  | 0
|  | T-09 | Add data from database into the Angular UI Grid | 3 | 1 | 2 | In Dev |  | 2
|  | T-10 | Unit Testing | 1 |  | 1 | Not Started |  | 1
|  | T-11 | Code Review | 1 |  | 1 | Not Started |  | 1
|  | T-12 | POC (SQL Queries and Backend) | 2 | 0 | 2 | Not Started
10
SSDMS-101*(Home Page AB) | 7.5 Hours | T-01 | Understand the business | 0.5 | 0.5 | 0 | Done | Done
|  | T-02 | Understand the forward and backward linkages | 0.5 | 0.5 | 0 | Done
|  | T-03 | Create the HTML and CSS structure | 4 | 2 | 2 | Done
|  | T-04 | Create a block diagram(Work-Flow) | 0.5 | 0.5 | 0 | Done
|  | T-05 | Unit Testing | 1 | 0.5 | 0.5 | Done
|  | T-06 | NG-Include to include files into master HTML | 2 | 0 | 2 | Not Started
|  | T-06 | Code Review | 1 | 0.5 | 0.5 | Done
5
0
0
0
0
0
0
0
0
0
0
0
0