## SSDMS 15, 21, 23, 26
Type | Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours | Status | Completion Date
Frontend (AB) | SSDMS-15 | 16 | T1 | Understand the why of the story | 1 | 1 | 0 | Done | 2017-03-07
| SSDMS-15 |  | T2 | Understand backward & Forward linkages | 1 | 1 | 0 | Done
| SSDMS-15 |  | T3 | Block diagram of entire code journey | 0.5 | 0.5 | 0 | Done
| SSDMS-15 |  | T4 | Understand the existing code | 1.5 | 1.5 | 0 | Done | 2017-04-07
| SSDMS-15 |  | T5 | Create necessary skeleton for making Assessment Body application status Table | 0.5 | 0.5 | 0 | Done
| SSDMS-15 |  | T6 | Create layout of HTML page | 0.5 | 0.5 | 0 | Done
| SSDMS-15 |  | T7 | Create ui grid table for application status | 1 | 1 | 0 | Done
| SSDMS-15 |  | T8 | Label Entities using JS | 1 | 1 | 0 | Done
| SSDMS-15 |  | T9 | Create Edit feature for editing Affiliation forms | 2 | 2 | 0 | Done | 2017-05-07
| SSDMS-15 |  | T10 | Function to perform Edit option | 2 | 2 | 0 | Done
| SSDMS-15 |  | T11 | Receive data from Backend & populate in Profile Creation page | 1.5 | 1.5 | 0 | Done
| SSDMS-15 |  | T12 | Check Application Status (Approved/ Rejected/ Pending) | 0.5 |  | 0.5 | Not Started
| SSDMS-15 |  | T13 | Open profile creation page | 1 | 1 | 0 | Done | 2017-05-07
| SSDMS-15 |  | T14 | Change Status to pending | 0.5 |  | 0.5 | Not Started
| SSDMS-15 |  | T15 | Unit Testing | 0.5 |  | 0.5 | Not Started
| SSDMS-15 |  | T16 | Code Review & Feedback | 0.5 |  | 0.5 | Not Started
| SSDMS-15 |  | T17 | Incorporate Feedback | 0.5 |  | 0.5 | Not Started
[6 empty] | Hours Left | 2.5
Backend (AB) | SSDMS-21 | 14.5 | T1 | Understand the why of the story | 1 | 1 | 0 | Done
| SSDMS-21 |  | T2 | Understand backward & Forward linkages | 1 | 1 | 0 | Done
| SSDMS-21 |  | T3 | Block diagram of entire code journey | 0.5 | 0.5 | 0 | Done
| SSDMS-21 |  | T4 | Understand the existing code | 1.5 |  | 1.5 | Not Started
| SSDMS-21 |  | T5 | Create Dummy DB | 1 |  | 1 | Not Started
| SSDMS-21 |  | T6 | Estabilish connection between Frontend & Backend | 2 |  | 2 | Not Started
| SSDMS-21 |  | T7 | Map Entities of DB to table columns(Frontend) | 2 |  | 2 | Not Started
| SSDMS-21 |  | T8 | Comment Column should be changed by input of SCGJ | 2 |  | 2 | Not Started
| SSDMS-21 |  | T9 | On click of Edit icon Affiliation form Controller should be called | 2 |  | 2 | Not Started
| SSDMS-21 |  | T10 | Unit Testing | 0.5 |  | 0.5 | Not Started
| SSDMS-21 |  | T11 | Code Review & Feedback | 0.5 |  | 0.5 | Not Started
| SSDMS-21 |  | T12 | Incorporate Feedback | 0.5 |  | 0.5 | Not Started
[6 empty] | Hours Left | 12
Frontend (TP) | SSDMS-23 | 15.5 | T1 | Understand the why of the story | 1 | 1 | 0 | Done | 2017-03-07
| SSDMS-23 |  | T2 | Understand backward & Forward linkages | 1 | 1 | 0 | Done
| SSDMS-23 |  | T3 | Block diagram of entire code journey | 0.5 | 0.5 | 0 | Done
| SSDMS-23 |  | T4 | Understand the existing code | 1.5 | 0.1 | 1.4 | Done | 2017-05-07
| SSDMS-23 |  | T5 | Create necessary skeleton for making Training Partner application status Table | 0.5 | 0.1 | 0.4 | Done
| SSDMS-23 |  | T6 | Create layout of HTML page | 0.5 | 0.1 | 0.4 | Done
| SSDMS-23 |  | T7 | Create ui grid table for application status | 0.5 | 0.1 | 0.4 | Done
| SSDMS-23 |  | T8 | Label Entities using JS | 1 | 0.1 | 0.9 | Done
| SSDMS-23 |  | T9 | Create Edit feature for editing Affiliation forms | 2 | 0.1 | 1.9 | Done
| SSDMS-23 |  | T10 | Function to perform Edit option | 2 | 0.1 | 1.9 | Done
| SSDMS-23 |  | T11 | Receive data from Backend & populate in Profile Creation page | 1.5 | 0.1 | 1.4 | Done
| SSDMS-23 |  | T12 | Check Application Status (Approved/ Rejected/ Pending) | 0.5 |  | 0.5 | Not Started
| SSDMS-23 |  | T13 | Open profile creation page | 1 | 1 | 0 | Done | 2017-05-07
| SSDMS-23 |  | T14 | Change Status to pending | 0.5 |  | 0.5 | Not Started
| SSDMS-23 |  | T15 | Unit Testing | 0.5 |  | 0.5 | Not Started
| SSDMS-23 |  | T16 | Code Review & Feedback | 0.5 |  | 0.5 | Not Started
| SSDMS-23 |  | T17 | Incorporate Feedback | 0.5 |  | 0.5 | Not Started
[6 empty] | Hours Left | 11.2
Backend (TP) | SSDMS-26 | 14.5 | T1 | Understand the why of the story | 1 | 1 | 0 | Not Started
| SSDMS-26 |  | T2 | Understand backward & Forward linkages | 1 | 1 | 0 | Not Started
| SSDMS-26 |  | T3 | Block diagram of entire code journey | 0.5 | 0.5 | 0 | Not Started
| SSDMS-26 |  | T4 | Understand the existing code | 1.5 |  | 1.5 | Not Started
| SSDMS-26 |  | T5 | Create Dummy DB | 1 |  | 1 | Not Started
| SSDMS-26 |  | T6 | Estabilish connection between Frontend & Backend | 2 |  | 2 | Not Started
| SSDMS-26 |  | T7 | Map Entities of DB to table columns(Frontend) | 2 |  | 2 | Not Started
| SSDMS-26 |  | T8 | Comment Column should be changed by input of SCGJ | 2 |  | 2 | Not Started
| SSDMS-26 |  | T9 | On click of Edit icon Affiliation form Controller should be called | 2 |  | 2 | Not Started
| SSDMS-26 |  | T10 | Unit Testing | 0.5 |  | 0.5 | Not Started
| SSDMS-26 |  | T11 | Code Review & Feedback | 0.5 |  | 0.5 | Not Started
| SSDMS-26 |  | T12 | Incorporate Feedback | 0.5 |  | 0.5 | Not Started
| Total | 60.5 |  |  |  | Hours Left | 12
Note on E7: Pranjal Kumar Singh: HTML divs, sections and colr, padding
Note on E40: Pranjal Kumar Singh: HTML divs, sections and colr, padding