## Name 4
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
SSDMS-11 | 43 | T-01 | Understand the 'WHY' of the story. | 1 |  | 1
|  | T-02 | Understand forward and backward linkages. | 1 |  | 1
|  | T-03 | Make block diagram of entire code journey. | 1 |  | 1
|  | T-04 | Finalze the required fields of TP,AB and grouping of fields in Accordions | 2
|  | T-05 | Develop technical understanding |  |  | 0
|  |  | i) Angular JS - How to make forms,buttons ,textboxes etc. | 6 |  | 6
|  |  | ii) BootStrap - How to make Accordions | 4 |  | 4
|  |  | ii) BootStrap - how to design using bootstrap | 6 |  | 6
|  | T-06 | Design page structure using HTML | 2 |  | 2
|  | T-07 | Add Design using Bootstrap | 6 |  | 6
|  | T-08 | Integrate and creating fields using AngularJS | 6 |  | 6
|  | T-09 | Add CSS to the page | 2 |  | 2
|  | T-10 | Unit Testing | 2 |  | 2
|  | T-11 | Code Review | 1 |  | 1
|  | T-12 | Incorporate Code Review changes | 1
|  |  | Buffer Time | 2 |  | 1
SSDMS-51 | 38 | T-01 | Understand the 'WHY' of the story. | 1 |  | 1
|  | T-02 | Understand forward and backward linkages. | 1 |  | 1
|  | T-03 | Make block diagram of entire code journey. | 1 |  | 1
|  | T-04 | Technical Understanding |  |  | 0
|  |  | i) Brushingup Concepts of SpringBoot | 1 |  | 1
|  |  | ii) Collaborate with the frontend team(deciding the controller's name and type of data to be outputted to every query) | 2 |  | 2
|  |  | iii) Write dynamic SQL queries | 4 |  | 4
|  | T-05 | Design the Controllers,Services for the SQL queries | 6 |  | 6
|  | T-06 | Create DTO's for all Queries | 6 |  | 6
|  | T-07 | Create DAO's for all Queries | 6 |  | 6
|  | T-08 | Debugg | 4 |  | 4
|  | T-09 | Unit Testing | 2 |  | 2
|  | T-10 | Code Review | 1 |  | 1
|  | T-11 | Incorporate Code Review changes | 1 |  | 1
|  |  | Buffer Time | 2 |  | 2
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0