## Name 5
Type | Story | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
Frontend | As a product owner, I want a dynamic page so that FAQ queries should be populated on the page | 39 | T1 | Develop basic Understanding of the FAQ Functionality | 2 | 2 | 0
|  |  | T2 | Create Structure of FAQ Page | 1 | 1 | 0
|  |  | T3 | Technical Understanding :
|  |  | T4 | HTML | 2 | 2 | 0
|  |  | T5 | CSS | 1 | 1 | 0
|  |  | T6 | AngularJS | 4 | 2 | 2
|  |  | T7 | UI Bootstrap | 4 | 2 | 2
|  |  | T8 | UI Grid | 3 | 1 | 2
|  |  | T9 | Create a block diagram of FAQ | 1 | 1 | 0
|  |  | T10 | Display FAQ Question using basic HTML | 4 |  | 4
|  |  | T11 | Creating Dropdown menu for dynamic selection | 3 |  | 3
|  |  | T12 | Creating a accordian button using UI Bootstrap | 3 |  | 3
|  |  | T13 | On clicking the selection button dynamic table should be populated | 6 |  | 6
|  |  | T14 | Design of the FAQ page should be done by Angular UI Bootstrap | 4 |  | 4
|  |  | T15 | Unit testing | 0.5 |  | 0.5
|  |  | T16 | Code Review & Feedback | 0.5 |  | 0.5
27