## Name 1
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
Import Certificate
SSDMS - 62 | 23 | T-1 | Understand the bigger picture of the story. (Why Part ???) To provide a feature for Certificate Import. | 1 | 0 | 1
|  | T-2 | Analysis (Create layout for search so that user can search). | 2 | 0 | 2
|  | T-3 | Create a Block Diagram. | 1 | 0 | 1
|  | T-4 | Pick Batch ID from Front-end for searching. | 1 | 0 | 1
|  | T-5 | Send Batch ID to Back-end. | 1 | 0 | 1
|  | T-6 | Receive data from Database. | 1 | 0 | 1
|  | T-7 | Implement Database SQL queries. | 1 | 0 | 1
|  | T-8 | Receive data sent by Database, SQL query. | 1 | 0 | 1
|  | T-9 | Send data to frontend. | 1 | 0 | 1
|  | T-10 | Receive detail of Batch ID. | 1 | 0 | 1
|  | T-11 | Populate the table with data received from Back-end. | 3 | 0 | 3
|  | T-12 | Import (window). | 1 | 0 | 1
|  | T-13 | Store the link of the file on the Database. | 1 | 0 | 1
|  | T-14 | Store the file on the Database. | 3 | 0 | 3
|  | T-15 | Unit Testing. | 1 | 0 | 1
|  | T-16 | Debugging. | 2 | 0 | 2
|  | T-17 | Code Review | 1 | 0 | 1
23
Download Certificate
SSDMS - 64 | 17 | T-1 | Understand the bigger picture of the story. (Why Part ???) To provide a feature for Certificate Import. | 1 | 0 | 1
|  | T-2 | Analysis (Create layout for search so that user can search). | 2 | 0 | 2
|  | T-3 | Create a Block Diagram. | 1 | 0 | 1
|  | T-4 | Create a Downlaod Button.(certificate) | 1 | 0 | 1
|  | T-5 | Send Batch ID to Back-end. | 2 | 0 | 2
|  | T-6 | Implement Database SQL queries. | 2 | 0 | 2
|  | T-7 | Receive data sent by Database, SQL query. | 1 | 0 | 1
|  | T-8 | Send data to frontend. | 3 | 0 | 3
|  | T-9 | Unit Testing. | 1 | 0 | 1
|  | T-10 | Debugging. | 2 | 0 | 2
|  | T-11 | Code Review | 1 | 0 | 1
17
Search - Manage registration
SSDMS - 66 | 21 | T-1 | Understand the bigger picture of the story. (Why Part ???) To provide a search feature for Batch and details regarding the Batch | 1 | 0 | 1
|  | T-2 | Analysis (Create layout for search so that user can search). | 2 | 0 | 2
|  | T-3 | Creating a Block Diagram. | 1 | 0 | 1
|  | T-4 | Pick Batch ID from Front-end for searching. | 1 | 0 | 1
|  | T-5 | Send Batch ID to Back-end. | 1 | 0 | 1
|  | T-6 | Receive data from Database. | 1 | 0 | 1
|  | T-7 | Implement Database SQL queries. | 1 | 0 | 1
|  | T-8 | Receive data sent by Database, SQL query. | 1 | 0 | 1
|  | T-9 | Send data to frontend. | 1 | 0 | 1
|  | T-10 | Receive detail of Batch ID. | 1 | 0 | 1
|  | T-11 | Populate the table with data received from Back-end. | 2 | 0 | 2
|  | T-12 | Unit Testing. | 1 | 0 | 1
|  | T-13 | Debugging. | 2 | 0 | 2
|  | T-14 | Code Review | 1 | 0 | 1
17
48.5
Note on G23: Rachit Goyal: Time estimation for the above Story.
Note on G38: Rachit Goyal: Time estimation for the above Story.
Note on G55: Rachit Goyal: Time estimation for the above Story.
Note on G56: Rachit Goyal: Total time Estimation of all the Stories.

## Name 2
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 3
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 4
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 5
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0