## Sheet1
Story Name | Story estimate | Task ID | Task Description | Planned hours | Hours burnt | Remaining hours
Login module | 15 | T-1 | Static-Html& Css | 3 | 5 | 0
|  | T-2 | Functioning-angular and java script | 5 |  | 4
|  | T-3 | Backend-Validations | 10 |  | 6