## SSDMS 15, 21, 23, 26
Type | Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
Frontend (AB) | SSDMS-15 | 9 | T1 | Existing code Understanding | 1.5 |  | 1.5
| SSDMS-15 |  | T2 | Create necessary skeleton for making Assessment Body status Table | 0.5 |  | 0.5
| SSDMS-15 |  | T3 | Create Divisions for AB status table | 0.5 |  | 0.5
| SSDMS-15 |  | T4 | Create basic structure of Table | 0.5 |  | 0.5
| SSDMS-15 |  | T5 | Label Entities using JS | 1 |  | 1
| SSDMS-15 |  | T6 | Create Edit feature for editing Affiliation forms | 2 |  | 2
| SSDMS-15 |  | T7 | Function to perform Edit option | 2 |  | 2
| SSDMS-15 |  | T8 | Connect frontend to the DB | 1 |  | 1
Backend (AB) | SSDMS-21 | 11 | T1 | Existing code Understanding | 1.5 |  | 1.5
| SSDMS-21 |  | T2 | Create Dummy DB | 1 |  | 1
| SSDMS-21 |  | T3 | Configure Application Local properties for JDBC Connectivity | 0.5 |  | 0.5
| SSDMS-21 |  | T4 | Make Springboot files(Controller, Service, Dao, Dto, Config, Yml) for fetch/ store/ populate data in DB | 2 |  | 2
| SSDMS-21 |  | T5 | Map Entities of DB to table columns(Frontend) | 2 |  | 2
| SSDMS-21 |  | T6 | Comment Column should be changed by input of SCGJ | 2 |  | 2
| SSDMS-21 |  | T7 | On click of Edit icon Affiliation form Controller should be called | 2 |  | 2
Frontend (TP) | SSDMS-23 | 9 | T1 | Existing code Understanding | 1.5 |  | 1.5
| SSDMS-23 |  | T2 | Create necessary skeleton for making Training Partner status Table | 0.5 |  | 0.5
| SSDMS-23 |  | T3 | Create Divisions for TP status table | 0.5 |  | 0.5
| SSDMS-23 |  | T4 | Create basic structure of Table | 0.5 |  | 0.5
| SSDMS-23 |  | T5 | Label Entities using JS | 1 |  | 1
| SSDMS-23 |  | T6 | Create Edit feature for editing Affiliation forms | 2 |  | 2
| SSDMS-23 |  | T7 | Function to perform Edit option | 2 |  | 2
| SSDMS-23 |  | T8 | Connect frontend to the DB | 1 |  | 1
Backend (TP) | SSDMS-26 | 9 | T1 | Existing code Understanding | 1.5 |  | 1.5
| SSDMS-26 |  | T2 | Create Dummy DB | 1 |  | 1
| SSDMS-26 |  | T3 | Configure Application Local properties for JDBC Connectivity | 0.5 |  | 0.5
| SSDMS-26 |  | T4 | Make Springboot files(Controller, Service, Dao, Dto, Config, Yml) for fetch/ store/ populate data in DB | 1 |  | 1
| SSDMS-26 |  | T5 | Map Entities of DB to table columns(Frontend) | 1.5 |  | 1.5
| SSDMS-26 |  | T6 | Comment Column should be changed by input of SCGJ | 1.5 |  | 1.5
| SSDMS-26 |  | T7 | On click of Edit icon Affiliation form Controller should be called | 2 |  | 2
| Total | 38