## Name 1
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
SSDMS-70* | 1 | T-1 | Business Understanding( Understanding purpose) |  |  | 0
|  | T-1-a | • Used to assign AB for assessment of a batch | 1 |  | 1
| 3 | T-2 | Forward and backward linkages (Understanding Linkages)
|  | T-2-a | • The SCGJ users can see the batches that to be proposed and propose an Assessment body for it | 0.5 |  | 0.5
|  | T-2-b | • Depending on the response from Assessment body tables are divided into three categories | 0.5 |  | 0.5
|  | T-2-c | 1. Propose table: On the basis of proposal by SCGJ, the details of batches and AB proposed are visible here | 0.5 |  | 0.5
|  | T-2-d | 2. Approve table : If assessment body confirms the assessment, the details of batches and AB are visible here | 0.5 |  | 0.5
|  | T-2-e | 3. Reject table: If assessment body denies the assessment, the details of batches and AB are visible here | 0.5 |  | 0.5
|  | T-2-f | • A withdraw functionality is also added to the Proposed batches table so that SCGJ users can withdraw the assignment from an AB | 0.5 |  | 0.5
| 24 | T-3 | Technical Understanding |  |  | 0
|  | T-3-a | • Learning: | 6 |  | 6
|  |  | Angular JS |  |  | 0
|  |  | Angular UI Grid |  |  | 0
|  |  | MySQL |  |  | 0
|  |  | JDBC |  |  | 0
|  | T-3-b | • Making Template and Tables | 4 |  | 4
|  | T-3-c | • Creating database | 4 |  | 4
|  | T-3-d | • Writing YML, config SQL and JDBC etc. | 10 |  | 10
| 2 | T-4 | Unit Testing | 2 |  | 2
| 0.5 | T-5 | Code review | 0.5 |  | 0.5
|  | T-6 | Incorporating changes |  |  | 0
Total | 30.5