## Name 1
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 2
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 3
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 4
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Name 5
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
SSDMS 45 | 7 | T01 | Designing select menu and upload button | 2 | 0 | 2
|  | T02 | Client side validations (checking .csv file format) | 3 | 0 | 3
|  | T03 | Designing controller of Angular | 2 | 0 | 2
SSDMS 46 | 41 | T01 | Create controller | 1 | 0 | 1
|  | T02 | Saving selected csv on local machine | 2 | 1 | 1
|  | T03 | Checking type of CSV(comparing column names) | 4 | 1 | 3
|  | T04 | If invalid : Delete the file from local machine & Exit | 1 | 0 | 1
|  |  | If valid : Validate the uploaded csv |  |  | 0
|  | T05 | Create DTO for each csv | 3 | 3 | 0
|  | T06 | Validating Candidate.csv | 4 | 3 | 1
|  | T07 | Validating Batch.csv | 4 | 3 | 1
|  | T08 | Validating Training_Partner.csv | 1 | 1 | 0
|  | T09 | Validating Centre.csv | 1 | 1 | 0
|  | T10 | Validating Trainer.csv | 1 | 1 | 0
|  | T11 | Validating Assessment_Agency.csv | 1 | 1 | 0
|  | T12 | Validating Assessor.csv | 1 | 1 | 0
|  | T13 | Validating Employer.csv | 1 | 1 | 0
|  | T14 | If invalid data : Delete the file from local machine & Exit | 0.5 | 0 | 0.5
|  | T15 | If valid data : Make connection with database | 0.5 | 0 | 0.5
|  | T16 | Program to run insert/update query | 1 | 0 | 1
|  | T17 | Coding DAO for each CSV | 5 | 0 | 5
|  | T18 | Coding Config class and .yml file | 3 | 0 | 3
|  | T19 | Integrating all modules with proper flow | 2 | 0 | 2
|  | T20 | Unit testing | 2 | 0 | 2
|  | T21 | Debugging | 2 | 0 | 2
SSDMS16, SSDMS17, SSDMS18, SSDMS19, SSDMS20 | 22 | T01 | Understanding exact Work flow of story | 1 |  | 1
|  | T02 | Program to fetch data from different tables + Creating SQL queries | 2 |  | 2
|  | T03 | Create controller & Service | 1 |  | 1
|  | T04 | Coding DAO for all 4 tables to fetch data | 3 |  | 3
|  | T05 | Coding config class and .yml file | 3 |  | 3
|  | T06 | Integrating data of all 4 tables in single object in service | 3 |  | 3
|  | T07 | Program functionality of accept/reject/show interest button | 1 |  | 1
|  | T08 | Coding respective DAO's for accept/reject/show interest functionality | 2 |  | 2
|  | T09 | Integrating all modules with proper flow | 2 |  | 2
|  | T10 | Unit Testing | 2 |  | 2
|  | T11 | Debugging | 2 |  | 2