## Sheet1
story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
SSDMS-14 | 22 hrs. | T_1 | Understanding 'WHY' of the story? To create a LOGOUT functionality so that the user can successfully exit the Profile Creation page. | 3 hrs
|  | T_2 | Understanding forward and backward linkages. BACKWARD:SCGJ user fill the LOGIN form and after he/she enters into the profile creation page .FORWARD: SCGJ user press the logout button,then he/she will forwarded to LOGIN page. | 6 hrs
|  | T-3 | Make block diagram of the entire code journey. | 2 hrs
|  | T_4 | Technical Understanding of the story. Which languages (Angular,Bootstarp) is used to implement the story . | 6 hrs
|  | T_5 | Unit Testing | 3 hrs
|  | T_6 | Code Review | 1 hrs
|  | T_7 | Incorporate code review comments. | 1 hrs
SSDMS-15 | 24 hrs | T_1 | Understanding 'WHY' of the story? To make a Batch Assignment table including a search option. | 4 hrs
|  | T_2 | Understanding forward and backward linkages. | 6 hrs
|  | T_3 | Make block diagram of the entire code journey. | 2 hrs
|  | T_4 | Technical Understanding of the story. Which languages (HTML) is used to implement the story . | 7 hrs
|  | T_5 | Unit Testing | 2 hrs
|  | T_6 | Code Review | 1 hrs
|  | T_7 | Incorporate code review comments. | 2 hrs