## Name 5
Story ID | Story Estimate | Task ID | Task Description | Planned Hours | Hours Burnt | Remaining Hours
DBA | 14 | Task-1 | Understand of basic mysql workbench. | 2 | 2 | 0
|  | Task-2 | Connect database ruchi's ma'am machine. | 1 | 1 | 0
|  | Task-3 | write create sql for each table. | 4 | 6 | -2
|  | Task-4 | for each sql return :- exicuted :- fix error if any :- if successful then save the file table in .sql. | 1 | 1 | 1
|  | Task-5 | Repeat the above for all tables. | 1 |  | 1
|  | Task-6 | Get sql reviewed by deepak(Peer review) | 1 |  | 1
|  | Task-7 | sent the reviewed file to ruchi ma'am. | 1 |  | 1
|  | Task-8 | make suitable changes in DB schema if required | 1 |  | 1
|  | Task-9 | create a master sql | 1 |  | 1
|  | Task-10 | test master sql or dummy schema | 1 |  | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0